# Orion Project Meeting Notes

Sample 2 fictional demonstration data. Names, dates and events are invented for application testing.

# Meeting context

Meeting date: 16 October 2026. Attendees: Dev, Neha, Kiran, Isha and Om. This review records current dependencies, unresolved decisions and assigned actions for the Orion Equipment Booking Portal.

# Progress reviewed

The requirements were approved on 8 October 2026 and the catalogue prototype was completed on 12 October 2026. The booking API and booking form remain in progress.

# Blockers and decisions

Current project blocker: the staging authentication service is unavailable. Integration testing cannot start until staging access is restored. This issue remains unresolved.

Pending decision: Dev has not approved the maximum booking duration. Approval is required before Neha can finalise booking validation. The cancellation policy also remains unresolved.

Dependency gap: the asset inventory export has not been supplied. Om cannot complete inventory import until this file is available. A delivery date for the export is not confirmed.

# Recorded action items

Action item: Om will restore staging access by 19 October 2026. Status: In progress.

Action item: Dev will approve the maximum booking duration by 17 October 2026. Status: Pending.

Action item: Neha will publish the booking API contract by 18 October 2026. Status: In progress.

Action item: arrange a cancellation-policy review. Owner and due date were not recorded. Status: Pending.

Action item: confirm a delivery date for the asset inventory export. Owner and due date were not recorded. Status: Pending.

# Delivery outlook

The pilot delivery date remains the baseline target of 28 October 2026. No revised delivery date is confirmed. The team has not established a delivery probability or an overall project health score.