# AI Project Meeting Notes

AI Project Intelligence & Risk Advisor

Project AIPI-DEMO-26 | Snapshot 2026-10-07 | Version 1.0

The fictional review on 2026-10-07 recorded two validation blockers and assigned the follow-up tasks below. No completed validation result is implied.

Fictional demo scenario for this application. This dataset is not a record of actual defects, approvals or historical M1-M4 work.

# Participants and decisions

Participants: Priya Menon, Neha Rao, Ravi Kumar, Meera Shah and Arjun Das. The review retained the existing technology stack, provider abstraction, workspace boundaries and health formula.

Decision: preserve document formats, exact source quotations and uncertainty labels. Keep Connected workflow and Export / Download on Overview only.

Decision: use the six AI Project demonstration documents together, with no ServiceDesk content, and review all nine named risk records without inventing missing ratings.

# Blockers and pending decisions

Blocker B-01: isolated QA workspace access is unavailable; workspace isolation checks in T-08 are blocked. Ravi Kumar is responsible for T-16 by 2026-10-08.

Blocker B-02: approved edge-case PDF and DOCX fixtures are missing; cross-format checks in T-09 are blocked. Priya Menon is responsible for T-17 by 2026-10-08.

Pending decision DEC-01: Priya Menon will select the mentor demonstration document set by 2026-10-08; selection remains pending at the snapshot.

# Assigned action items

Action item: Golden-source retrieval checks; Owner: Neha Rao; Due date: 2026-10-10; Status: In progress; Dependency: T-02; Task ID: T-07.

Action item: Workspace isolation checks; Owner: Ravi Kumar; Due date: 2026-10-09; Status: Blocked; Dependency: B-01; Task ID: T-08.

Action item: Cross-format ingestion checks; Owner: Meera Shah; Due date: 2026-10-10; Status: Blocked; Dependency: B-02; Task ID: T-09.

Action item: Incremental upload race checks; Owner: Arjun Das; Due date: 2026-10-12; Status: In progress; Dependency: T-06; Task ID: T-10.

Action item: Explicit risk-language checks; Owner: Neha Rao; Due date: 2026-10-13; Status: Not started; Dependency: T-06; Task ID: T-11.

Action item: Offline provider setup checks; Owner: Ravi Kumar; Due date: 2026-10-13; Status: Not started; Dependency: T-06; Task ID: T-12.

Action item: PDF and Word evidence checks; Owner: Arjun Das; Due date: 2026-10-14; Status: Not started; Dependency: T-06; Task ID: T-13.

Action item: Mobile and long-text checks; Owner: Arjun Das; Due date: 2026-10-15; Status: Not started; Dependency: T-06; Task ID: T-14.

Action item: Unsupported-question checks; Owner: Meera Shah; Due date: 2026-10-14; Status: Not started; Dependency: T-06; Task ID: T-15.

Action item: Provide isolated QA workspace access; Owner: Ravi Kumar; Due date: 2026-10-08; Status: In progress; Dependency: Not stated; Task ID: T-16.

Action item: Provide approved edge-case documents; Owner: Priya Menon; Due date: 2026-10-08; Status: In progress; Dependency: Not stated; Task ID: T-17.

Action item: Review mentor demonstration readiness; Owner: Priya Menon; Due date: 2026-10-16; Status: Not started; Dependency: T-07 through T-15; Task ID: T-18.

# Unknown information

Action item: review a future scanned-PDF policy; Owner: Not stated; Due date: Not stated; Status: Pending review. OCR is outside the current scope. This review is not a commitment to implement it.

Delivery forecast: the mentor demonstration target remains 2026-10-19; readiness depends on the D-02 and D-03 validation reviews. No revised delivery date is confirmed. Overall delivery probability is Not stated.